## Project schedule
| Project 3 | [5 empty] | Project start: | [7 empty] | 2026-02-27
| Group 12 | Section 151 |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-02-27 | [6 empty] | 2026-03-06 | [6 empty] | 2026-03-27
| TASK | ASSIGNED TO | PROGRESS | START | END |  | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19
[7 empty] | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Writing
| A Timesheet | Whole Group, each uploading their resepctive time | 50% | 2026-02-27 | 2026-03-02 | 4
| Annototated Code Document | Ben, Tessa, Cam | 100% | 2026-03-22 | 2026-03-24 | 3
| Scope of Work | Tessa, Ben, Macy |  | 2026-03-24 | 2026-03-28 | 5
Client Request
| Bar chart information and all the variables that go along with it | Macy | 100% | 2026-02-27 | 2026-03-03 | 5
| Trajectory Calculations and Simulations | Tessa, Cam | 100% | 2026-03-09 | 2026-03-14 | 6
| Simulation Study | Ben Wehrbein | 100% | 2026-03-14 | 2026-03-17 | 4
|  |  |  | 2026-03-14 | 2026-03-16 | 3
Report
| Results and Discussion | Macy | 100% | 2026-03-22 | 2026-03-27 | 6
| Methods | Ben | 80% | 2026-03-28 | 2026-04-01 | 5
| Introduction | Ben | 80% | 2026-03-10 | 2026-03-15 | 6
| References | Macy, Ben | 10% | 2026-02-20 | 2026-02-24 | 5
GitHub
| READ ME | Macy | 20% | 2026-03-27 | 2026-02-28 | -26
| Compiling GitHub | Macy | 100% | 2026-03-02 | 2026-03-14 | 13
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]